## Summary
Stale work cleanup: App squad
Open PRs, open branches and issues in progress. Stale means: a PR open more than 7 days, a branch without a PR older than 14 days, an issue in progress more than twice the 90-day average cycle time (3d 1h, so 6d 2h). Source: DevStats MCP.
ACTION | PRS | BRANCHES | ISSUES | TOTAL
Close | 0 | 12 | 2 | 14
Nudge | 0 | 0 | 0 | 0
Split | 0 | 0 | 0 | 0
Unblock | 0 | 0 | 0 | 0
Fix the status | 0 | 0 | 1 | 1
Keep | 7 | 13 | 2 | 22
All items | 7 | 25 | 5 | 37
REPOSITORY | PRS | BRANCHES
devstats | 7 | 25
All 5 issues are in the Development project.
THREE PATTERNS WORTH DISCUSSING
1. The PR queue is clean. The stale work never became a PR.
0 of the 7 open PRs are stale: the oldest is 2 days old. But 12 of the 17 branches still in coding are older than 14 days, the oldest 98. This is work nobody can see or review. One rule fixes most of it: a branch gets a draft PR within a few days, or it goes.
2. Parked issues still count as in progress.
3 of the 5 issues listed as in progress are sitting in Todo or Backlog on the board, and have been for 130 to 304 days. They were started once and never resolved, so every aging report keeps them at the top. Cancel or reschedule them and the aging list becomes useful again.
3. Private, for a 1:1 and not for the cleanup hour.
8 of the 12 stale branches and 5 of the 7 open PRs belong to one person (dev-3). That is a load signal, not a discipline problem: many small fixes started between bigger tasks, none finished. Ask what keeps interrupting them.

## PRs
PR | LINK | OWNER | AGE (DAYS) | STAGE | SIZE (LINES) | ACTION | REASON
#7539 SUP2-965: DEMO - GitHub Copilot | Open | dev-1 | 2 | Merge | 565 | Keep | Reviewed 3 times and waiting for merge. Merge it.
#7545 SUP2-962: Duplicated column while configuring Done columns | Open | dev-2 | 1 | Review | 385 | Keep | First review is in. Moving.
#7547 SUP2-969: Filter WorkBoard objectives by a workspace-configured team_id setting | Open | dev-3 | 1 | Pickup | 107 | Keep | Small and 1 day old, but nobody is assigned to review it. Name a reviewer today so it never reaches the Nudge line.
#7550 SUP2-975: Add MCP Tool for Claude Activity report | Open | dev-3 | 0 | Pickup | 174 | Keep | One of three sibling PRs of 174 lines opened within minutes. Review the three in one sitting, by one person.
#7551 SUP2-976: Add MCP Tool for Cursor Activity report | Open | dev-3 | 0 | Pickup | 174 | Keep | One of three sibling PRs of 174 lines opened within minutes. Review the three in one sitting, by one person.
#7552 SUP2-977: Add MCP Tool for Devin Activity report | Open | dev-3 | 0 | Pickup | 174 | Keep | One of three sibling PRs of 174 lines opened within minutes. Review the three in one sitting, by one person.
#7553 Remove AiUsageTool MCP tool | Open | dev-3 | 0 | Pickup | 138 | Keep | Opened today. No reviewer assigned yet.

## Branches
BRANCH | LINK | OWNER | AGE (DAYS) | STAGE | SIZE (LINES) | ACTION | REASON
fix/aikido-security-update-packages-48565083-oj7w |  | web-flow | 98 | Coding (no PR) |  | Close | Automated security update that never became a PR. A newer update branch, 4 days old, replaces it.
fix/aikido-security-update-packages-51784609-opft |  | web-flow | 92 | Coding (no PR) |  | Close | Automated security update that never became a PR. A newer update branch, 4 days old, replaces it.
feature/sup2-812-fix-off-by-one-overlap-between-current-and-previous-period |  | dev-3 | 79 | Coding (no PR) |  | Close | Oldest human branch in the squad, no PR. If the fix still matters, redo it on a fresh branch: rebasing 79 days of main costs more than the fix.
feature/dev-3906-add-integration-github |  | dev-3 | 58 | Coding (no PR) |  | Close | Started the same day as its twin integration branch, no PR since. Looks like a spike. Confirm with the owner and delete, or move the idea to an issue.
feature/dev-3907-add-integration-gitlab |  | dev-3 | 58 | Coding (no PR) |  | Close | Started the same day as its twin integration branch, no PR since. Looks like a spike. Confirm with the owner and delete, or move the idea to an issue.
chore/delete-dead-component-tests-2 |  | dev-4 | 52 | Coding (no PR) |  | Close | Second attempt at a cleanup chore, no PR. A cleanup that waited 52 days is cheaper to redo than to rebase.
feature/dev-3998-azure-repos-pat-info-icon |  | dev-3 | 46 | Coding (no PR) |  | Close | Small UI change with no PR after 46 days. Either it shipped another way or nobody needs it.
fix/github-projects-syncing-lock-key |  | dev-3 | 39 | Coding (no PR) |  | Close | A fix with no PR for 39 days. If the bug is still there it needs an issue and a fresh branch. If it is not, delete.
fix/copilot-org-availability-lookback-window |  | dev-3 | 37 | Coding (no PR) |  | Close | A fix with no PR for 37 days. If the bug is still there it needs an issue and a fresh branch. If it is not, delete.
fix/cursor-cmdk-requests-card-case-mismatch |  | dev-3 | 23 | Coding (no PR) |  | Close | Just past the 14-day line. The owner opens a PR before the cleanup hour, or the branch is deleted in it.
fix/livewire-lazy-load-scroll-race |  | dev-3 | 22 | Coding (no PR) |  | Close | Just past the 14-day line. The owner opens a PR before the cleanup hour, or the branch is deleted in it.
chore/plan-comparison-command |  | dev-4 | 21 | Coding (no PR) |  | Close | Just past the 14-day line. The owner opens a PR before the cleanup hour, or the branch is deleted in it.
fix/code-review-controls-panel-margin |  | dev-1 | 9 | Coding (no PR) |  | Keep | Under the 14-day line, but already red in Aging Branches. Open a draft PR so the work is visible.
feature/dev-4241-kiosk-mcp-provision-the-passport-personal-access-grant |  | dev-1 | 7 | Review |  | Keep | In review and yellow in Aging Branches. The one to watch this week.
feature/dev-4303-planning-accuracy-unify-sprint-weighted-vs-task-weighted |  | dev-1 | 7 | Coding (no PR) |  | Keep | In coding for 7 days, yellow in Aging Branches. Recent and tied to an issue.
fix/aikido-security-update-packages-114285701-vkzu |  | web-flow | 4 | Coding (no PR) |  | Keep | The current automated security update. Merge it and the two old ones can go.
chore/sup2-955-add-github-dependabot-to-devstats-repository |  | dev-1 | 3 | Coding (no PR) |  | Keep | Recent and moving.
feature/sup2-965-demo-github-copilot |  | dev-1 | 2 | Merge |  | Keep | Has an open PR. See the PRs sheet.
support/sup2-962-duplicated-column-while-configuring-done-columns |  | dev-2 | 1 | Review |  | Keep | Has an open PR. See the PRs sheet.
feature/sup2-969-filter-workboard-objectives-by-a-workspace-configured |  | dev-3 | 1 | Pickup |  | Keep | Has an open PR. See the PRs sheet.
feature/sup2-975-add-mcp-tool-for-claude-activity-report |  | dev-3 | 0 | Pickup |  | Keep | Has an open PR. See the PRs sheet.
feature/sup2-976-add-mcp-tool-for-cursor-activity-report |  | dev-3 | 0 | Pickup |  | Keep | Has an open PR. See the PRs sheet.
feature/sup2-977-add-mcp-tool-for-devin-activity-report |  | dev-3 | 0 | Pickup |  | Keep | Has an open PR. See the PRs sheet.
chore/remove-ai-usage-tool |  | dev-3 | 0 | Pickup |  | Keep | Has an open PR. See the PRs sheet.
enhancement/sup2-940-clickup-enhance-rate-limit-exception |  | (no author) | 0 | Coding (no PR) |  | Keep | Started today.

## Issues
ISSUE | LINK | OWNER | AGE (DAYS) | STAGE | SIZE (LINES) | ACTION | REASON
DEV-3366 (customer) - Index GitHub user full name in searches (converted to project) |  | dev-2 | 308 | Backlog |  | Close | Worked on for 4d 0h, then sent to Backlog 304 days ago. The title says it was converted to a project. It was never resolved, so it still counts as in progress. Close it.
DEV-3527 Cursor Integration - Implement Cursor integration form with API key validation |  | dev-3 | 178 | Todo |  | Close | 26d 23h in progress across two stretches, then back to Todo 130 days ago. No open branch for it, while the Cursor report already has a fix branch of its own. Confirm the form shipped another way and close.
DEV-3211 Settings V3 - Remove deploy by TAG |  | dev-1 | 234 | Todo |  | Fix the status | In progress for 20h 58m, then back to Todo 219 days ago. No open branch or PR. Schedule it or cancel it. Until then it sits at the top of every aging list.
DEV-4334 Rewrite prompt library prompts |  | dev-4 | 1 | In Review |  | Keep | Recent and moving.
DEV-4335 Generate real outputs for prompts — batch A |  | dev-4 | 0 | In Review |  | Keep | Recent and moving.

## Message
MESSAGE TO SCHEDULE THE CLEANUP HOUR
Cleanup hour this week. The list has 37 items and 22 of them need nothing from us.
14 we can simply close: 12 branches that never became a PR (the oldest is 98 days old) and 2 issues that were parked long ago.
Before the meeting, filter the Branches sheet by your name. For each row marked Close: open a PR, or tell me it can go.
DEV-3211 needs a decision from its owner: schedule it or cancel it.
No open PR is stale today. To keep it that way, every PR gets a reviewer the moment it is opened.